## Tasks
SpecAlive - Implementation Task Plan
Legend: fill the yellow Owner column (dropdown: Arthesh / Parth / Yasmeen / All), e.g. Owner = Parth. Status and Target Day are editable. M = must-have for Floor/Solid tier on L1, S = stretch. Phase / Spec Doc: the phase in docs/implementation_plan.md and its specification in docs/specifications/ (one phase = one spec = one pull request). Hours are rough single-person estimates (source: planning discussion).
ID | Workstream | Phase | Spec Doc | Task | Deliverable / Done when | Est. Hrs | Priority | Depends On | Owner | Target Day | Status | Notes
T0.1 | 0 - Setup | Phase 1 | FR-01-foundation.md | Repo skeleton: Python package, pyproject, CLI entry 'specalive run <bundle_dir> -o out/', DECISIONS.md, AI-LOG.md | 'specalive --help' runs; first DECISIONS entry committed | 1 | M | - |  | Day 1 | Not started
T0.2 | 0 - Setup | Phase 1 | FR-01-foundation.md | Install OpenModelica toolchain (omc) + MSL 4.x | omc compiles and simulates MSL ControlledTanks example from a script | 1.5 | M | - |  | Day 1 | Not started
T0.3 | 0 - Setup | Phase 1 | FR-01-foundation.md | SysML v2 validator spike: OMG Pilot Implementation (Jupyter kernel) vs one alternative | Hand-written .sysml with parts, ports, connections and a state machine parses from command line; choice logged in DECISIONS | 2 | M | - |  | Day 1 | Not started
T0.4 | 0 - Setup | Phase 1 | FR-01-foundation.md | OpenAI wrapper: structured outputs from Pydantic schemas, temperature 0, disk cache of responses | Same prompt returns identical cached result; token/cost log | 1 | M | T0.1 |  | Day 1 | Not started
T1.1 | 1 - Shared foundation | Phase 2 | FR-02-ir-and-catalogue.md | IR schema (Pydantic): Part, Port (direction, domain), Connection, Parameter (value, unit, status, authority), StateMachine (states, transitions, parallel regions), Requirement, Assumption, Question, Conflict, TraceLink, confidence | Schema frozen, JSON Schema exported; the one contract between workstreams. All three sign off | 2 | M | T0.1 |  | Day 1 | Not started
T1.2 | 1 - Shared foundation | Phase 2 | FR-02-ir-and-catalogue.md | Golden IR for L1 Tank, hand-written from the test-case docs | Validates against schema; fixture for generators and reference for coverage scoring | 1.5 | M | T1.1 |  | Day 1 | Not started
T1.3 | 1 - Shared foundation | Phase 10 | FR-10-l2-feedback-extension.md | Golden IR for L2 Room CO2 | Validates against schema | 1.5 | S | T1.1 |  | Day 2 | Not started
T1.4 | 1 - Shared foundation | Phase 2 | FR-02-ir-and-catalogue.md | Component catalogue: IR part kind -> MSL class + SysML part def + port mapping (tank->OpenTank, valve->ValveDiscrete, room->ClosedVolume, flux tube->FluxTubes.*) | YAML/JSON catalogue; LLM may only pick from it (domain-knowledge injection, prevents invented components) | 2 | M | T1.1, T0.2 |  | Day 1 | Not started
A1 | A - Ingestion & extraction | Phase 3 | FR-03-evidence-ingestion.md | File readers -> EvidenceChunk{source, locator, text}: pdf, docx, xlsx (all sheets), eml, md/txt, .mo, .puml, json, csv (header+stats), png (vision or flagged) | All 4 test bundles load without crash; unreadable files reported, never silently dropped | 3 | M | T0.1 |  | Day 1-2 | Not started
A2 | A - Ingestion & extraction | Phase 3 | FR-03-evidence-ingestion.md | Source classification: type, revision, date, reliability (use Source_Index sheet if present, else heuristics/LLM) | Every chunk carries reliability and authority rank | 1.5 | M | A1 |  | Day 2 | Not started
A3 | A - Ingestion & extraction | Phase 4 | FR-04-extraction-and-resolution.md | LLM extraction: chunks -> IR fragments (parts, params, connections, requirements, states) with supporting quote | Fragments validate against schema; every fragment has a TraceLink | 3 | M | A2, T1.1, T0.4 |  | Day 2 | Not started
A4 | A - Ingestion & extraction | Phase 4 | FR-04-extraction-and-resolution.md | Merge & entity resolution: alias unification (tank1 = TK-101 = T1), de-duplication | One node per real component on L1 | 2 | M | A3 |  | Day 2 | Not started
A5 | A - Ingestion & extraction | Phase 4 | FR-04-extraction-and-resolution.md | Conflict & precedence resolver: approved CR > design review decision > baseline spec > legacy model / informal notes; log Conflict with rationale; unresolvable -> Question | L1 yields 0.80 m and 10/12/8 s with both conflicts logged | 2.5 | M | A4 |  | Day 2 | Not started
A6 | A - Ingestion & extraction | Phase 4 | FR-04-extraction-and-resolution.md | Assumptions, gaps & honesty gate: implicit conventions and missing units/ICs -> Assumption or Question; reject elements with neither trace nor assumption | Honesty check passes; missing-info list produced | 1.5 | M | A5 |  | Day 2 | Not started
A7 | A - Ingestion & extraction | Phase 4 | FR-04-extraction-and-resolution.md | Interactive clarifying questions in CLI (--interactive); otherwise declared defaults | A question asked, answered and reflected in IR + trace | 1 | S | A6 |  | Day 3 | Not started
A8 | A - Ingestion & extraction | Phase 4 | FR-04-extraction-and-resolution.md | Plain-text input path: single prose paragraph -> IR (judge-supplied spec) | 1-paragraph spec produces valid IR in < 2 min | 1 | M | A3 |  | Day 2-3 | Not started
B1 | B - Generators & compile | Phase 5 | FR-05-sysml-generation.md | SysML v2 emitter (Jinja2, deterministic): package, part defs/usages, port defs, connections, attributes with SI units, requirement defs + satisfy, state defs + transitions, parallel regions; IR ids/traces as doc/metadata | L1 golden IR -> .sysml covering 3+ element types | 3 | M | T1.2, T1.4 |  | Day 2 | Not started
B2 | B - Generators & compile | Phase 5 | FR-05-sysml-generation.md | SysML validation hook using the validator chosen in T0.3 | Structured pass/fail + errors | 1 | M | B1, T0.3 |  | Day 2 | Not started
B3 | B - Generators & compile | Phase 6 | FR-06-modelica-generation.md | Modelica emitter: IR + catalogue -> .mo using MSL components, connect() equations, parameters with units, experiment(StopTime), IR ids in comments | L1 golden IR -> .mo | 4 | M | T1.2, T1.4, T0.2 |  | Day 2 | Not started
B4 | B - Generators & compile | Phase 6 | FR-06-modelica-generation.md | Controller / state-machine generation: enumeration state + when/algorithm, timers, command priority, interlocks as assert | L1 controller compiles, covers PAUSED/SHUTDOWN semantics | 3 | M | B3 |  | Day 2 | Not started
B5 | B - Generators & compile | Phase 6 | FR-06-modelica-generation.md | Compile & repair loop: .mos (loadModel, checkModel, buildModel), parse errors, deterministic fixes first then LLM repair (max 3), repair may NOT change topology, log every attempt | L1 compiles; repair log feeds AI-LOG entries | 3 | M | B4, T0.4 |  | Day 2-3 | Not started
B6 | B - Generators & compile | Phase 8 | FR-08-reports-and-traceability.md | Correspondence table: IR id <-> SysML element <-> Modelica component | Generated table proves layer consistency (needed for Full tier) | 1 | M | B1, B3 |  | Day 3 | Not started
B7 | B - Generators & compile | Phase 10 | FR-10-l2-feedback-extension.md | Continuous feedback pattern for L2 (sensor -> gain -> P controller -> source), trace substances | L2 golden IR compiles and simulates | 3 | S | T1.3, B5 |  | Day 3 | Not started
C1 | C - Verification & CLI | Phase 7 | FR-07-simulation-and-verification.md | Simulation runner: omc simulate -> results CSV/DataFrame | L1 simulates for 900 s | 1.5 | M | T0.2 |  | Day 1-2 | Not started
C2 | C - Verification & CLI | Phase 7 | FR-07-simulation-and-verification.md | Reference comparison: map result columns to reference CSV, state timing within tolerance, acceptance criteria (e.g. TP-17 AC-01..08) as executable checks | Pass/fail per acceptance criterion on L1 | 3 | M | C1 |  | Day 2 | Not started
C3 | C - Verification & CLI | Phase 7 | FR-07-simulation-and-verification.md | Structural coverage & repeatability: generated IR vs golden IR (% element coverage, 80% target); run twice, diff topology | Coverage % and repeatability verdict printed | 2 | M | T1.2 |  | Day 2 | Not started
C4 | C - Verification & CLI | Phase 8 | FR-08-reports-and-traceability.md | Reports: summary.md (1-minute read), traceability.md, assumptions.md (assumptions, conflicts, questions), matplotlib plots | Generated per run in out/<case>/ | 2 | M | C2, C3 |  | Day 2-3 | Not started
C5 | C - Verification & CLI | Phase 9 | FR-09-cli-and-end-to-end.md | CLI orchestration: staged pipeline with live progress (rich), output layout, exit codes, graceful failure on bad input | 'specalive run Testcases/tank...' runs end to end with progress | 2 | M | A6, B5, C4 |  | Day 3 | Not started
C6 | C - Verification & CLI | Phase 9 | FR-09-cli-and-end-to-end.md | Adversarial / judge-spec rehearsal: 3 unseen specs (plain-text heated tank, contradictory spec, missing units) | Results recorded; bugs fed back to A and B | 2 | M | C5 |  | Day 3 | Not started
P1 | P - Process | Not a phase | FR-11-nonfunctional-and-submission.md | DECISIONS.md: one commit per day with rejected alternatives | Entry committed every day | 0.75 | M | - |  | Daily | Not started
P2 | P - Process | Not a phase | FR-11-nonfunctional-and-submission.md | AI-LOG.md: at least 2 real overrides (repair loop, extraction errors, invented MSL components) | 2+ explainable override cases | 1 | M | A3, B5 |  | Day 3 | Not started
P3 | P - Process | Not a phase | FR-11-nonfunctional-and-submission.md | Domain expert conversation; record what changed | Documented delta (scope cut / reframing / assumption killed) | 1 | M | - |  | Day 1 | Not started
P4 | P - Process | Not a phase | FR-11-nonfunctional-and-submission.md | Architecture note / diagram | Pipeline + key decisions on one page | 1 | M | T1.1 |  | Day 3 | Not started
P5 | P - Process | Not a phase | FR-11-nonfunctional-and-submission.md | Deck of at most 8 slides + demo rehearsal on unseen spec | Deck done; demo runs within slot | 2 | M | C6 |  | Day 3 | Not started
Total estimated hours

## Summary
Workload Summary (updates from the Tasks sheet)
Owner | Tasks | Total Hrs | Must-have Hrs | Stretch Hrs | Done Tasks
Arthesh
Parth
Yasmeen
All
Unassigned
Total
Phase | Tasks | Total Hrs | Must-have Hrs | Stretch Hrs | Done Tasks | Spec Doc
Phase 1 | [5 empty] | FR-01-foundation.md
Phase 2 | [5 empty] | FR-02-ir-and-catalogue.md
Phase 3 | [5 empty] | FR-03-evidence-ingestion.md
Phase 4 | [5 empty] | FR-04-extraction-and-resolution.md
Phase 5 | [5 empty] | FR-05-sysml-generation.md
Phase 6 | [5 empty] | FR-06-modelica-generation.md
Phase 7 | [5 empty] | FR-07-simulation-and-verification.md
Phase 8 | [5 empty] | FR-08-reports-and-traceability.md
Phase 9 | [5 empty] | FR-09-cli-and-end-to-end.md
Phase 10 | [5 empty] | FR-10-l2-feedback-extension.md
Not a phase | [5 empty] | FR-11-nonfunctional-and-submission.md
Workstream | Tasks | Total Hrs | Must-have Hrs | Stretch Hrs | Done Tasks
0 - Setup
1 - Shared foundation
A - Ingestion & extraction
B - Generators & compile
C - Verification & CLI
P - Process
Note: 'All' = shared tasks (e.g. T1.1 IR schema sign-off). 'Not a phase' = cross-cutting process work governed by FR-11. Hours come from the Est. Hrs column on the Tasks sheet.

## Phases
Phase -> Specification -> Tasks (one phase = one spec = one pull request)
Phase | Name | Spec Doc | Track | Starts after | Target Day | Task IDs
Phase 1 | Foundation | FR-01-foundation.md | Setup | - | Day 1 | T0.1, T0.2, T0.3, T0.4
Phase 2 | IR schema, catalogue, golden IR | FR-02-ir-and-catalogue.md | Shared | Phase 1 | Day 1 | T1.1, T1.2, T1.4
Phase 3 | Evidence ingestion | FR-03-evidence-ingestion.md | A | Phase 2 | Day 1-2 | A1, A2
Phase 4 | Extraction and resolution | FR-04-extraction-and-resolution.md | A | Phase 3 | Day 2 | A3, A4, A5, A6, A7, A8
Phase 5 | SysML v2 generation | FR-05-sysml-generation.md | B | Phase 2 | Day 2 | B1, B2
Phase 6 | Modelica generation and compile loop | FR-06-modelica-generation.md | B | Phase 2 | Day 2-3 | B3, B4, B5
Phase 7 | Simulation and verification | FR-07-simulation-and-verification.md | C | Phase 2 | Day 1-2 | C1, C2, C3
Phase 8 | Reports and traceability | FR-08-reports-and-traceability.md | C (+B6) | Phases 5, 6, 7 | Day 2-3 | B6, C4
Phase 9 | CLI and end to end | FR-09-cli-and-end-to-end.md | C | Phases 4, 6, 8 | Day 3 | C5, C6
Phase 10 | L2 feedback extension (stretch) | FR-10-l2-feedback-extension.md | Shared / B | Phase 9 | Day 3 | T1.3, B7
Not a phase | Non-functional and submission (cross-cutting) | FR-11-nonfunctional-and-submission.md | Process | applies to all | Daily | P1, P2, P3, P4, P5
Tracks A, B and C run in parallel once Phase 2 lands; within a track the phases are sequential.
Also in docs/specifications/: specindex.md (index) and FR-12-not-delivered.md (L3/L4, web UI, round-trip editing - no tasks).

## Dependencies
Critical path and scope notes
T0.x -> T1.1 -> A1 -> A2 -> A3 -> A4 -> A5 -> A6 ----------------------+
T1.1 -> T1.2/T1.4 -> B1 -> B2 ; B3 -> B4 -> B5 -> B6 ---------+--> C5 end-to-end -> C6 -> P5
T0.2 -> C1 (on MSL example) -> C2 -> C3 -> C4 ------------------+
Day 1: Phase 1 + Phase 2 (the IR schema is the contract - freeze it first).
Day 2: Tracks A (Phases 3-4), B (Phases 5-6), C (Phases 7-8) in parallel against the golden IR, so nobody waits on extraction.
Day 3: Phase 9 - integrate on L1, run C6 on unseen specs, prepare deck and demo. Phase 10 only if time allows.
Biggest risks: T0.2 (omc + MSL) and T0.3 (SysML v2 validator) - tool friction sinks teams; settle on day 1.
Cut rule: drop Phase 10 (T1.3, B7) and A7 before dropping C2 or C6. One case end to end, verified against acceptance criteria and robust to an unseen spec, beats breadth.